CRASH LENS

Infrastructure Migration Master Plan

From GitHub Actions + Hostinger + Firebase

To AWS + Cloudflare R2 + Supabase

Prepared for: Murad, Director of Traffic Engineering

AiCreatesAi.com

March 2026

# Executive Summary

This master plan outlines the complete infrastructure migration for CRASH LENS, transitioning from the current stack (GitHub Actions + Coolify on Hostinger + Firebase Auth) to a production-grade, government-ready architecture (AWS EC2 + Cloudflare R2 + Supabase + optimized GitHub Actions).

The migration is divided into five phases, each designed to be completed independently with zero downtime. Each phase includes the specific tools to use (Claude Chat MCP connectors, Claude Code, Terraform, CLI tools) and step-by-step instructions.

Architecture Comparison

| Layer | Current Stack | Target Stack |
| --- | --- | --- |
| Hosting | Coolify on Hostinger VPS | Coolify on AWS EC2 |
| File Storage | Cloudflare R2 (via GitHub Actions) | Cloudflare R2 (via Workers + GitHub Actions) |
| Database | None (files in R2) | Supabase PostgreSQL |
| Auth | Firebase Auth | Supabase Auth |
| API Layer | Custom / none | Supabase PostgREST (auto-generated) |
| Data Pipeline | GitHub Actions only | GitHub Actions + Cloudflare Workers |
| DNS / CDN | Cloudflare | Cloudflare (unchanged) |

# Migration Timeline Overview

Estimated total duration: 6-8 weeks. Phases can overlap where indicated.

| Phase | Description | Duration | Priority | Primary Tool |
| --- | --- | --- | --- | --- |
| 1 | Cloudflare R2 Pipeline Enhancement | 1-2 weeks | HIGH | Claude Code + Wrangler |
| 2 | Supabase Setup + Schema Design | 1 week | HIGH | Claude Chat MCP |
| 3 | Firebase to Supabase Auth Migration | 1-2 weeks | HIGH | Claude Code + Scripts |
| 4 | Coolify Migration: Hostinger to AWS | 1 week | MEDIUM | AWS Console + SSH |
| 5 | Integration, Testing + Go-Live | 1-2 weeks | HIGH | All tools |

# Tools Reference Guide

Below is every tool you will use across all phases, with what each is best for.

| Tool | What It Does | Used In Phase(s) |
| --- | --- | --- |
| Claude Chat (MCP) | Cloudflare R2 + Supabase connectors built-in. Create buckets, run SQL, test configs interactively. | 1, 2, 5 |
| Claude Code | Agentic coding in your GitHub repo. Writes Workers, migration scripts, frontend code changes. | 1, 2, 3, 5 |
| Wrangler CLI | Cloudflare official CLI. Deploy Workers, manage R2 buckets, configure cron triggers. | 1 |
| Supabase CLI | Local development, database migrations, edge function deployment. | 2, 3 |
| Firebase CLI | Export auth users, get password hash params, download service account keys. | 3 |
| AWS Console / CLI | Launch EC2, configure security groups, allocate Elastic IP, manage EBS volumes. | 4 |
| Terraform (Optional) | Infrastructure-as-code for AWS. Reproducible EC2 + security group setup. | 4 |
| GitHub Actions | Existing crash data pipeline. Keep running, enhance with R2 upload steps. | 1, 5 |
| SSH / SCP | Transfer Coolify backups, Docker volumes, SSH keys between servers. | 4 |

PHASE 1

# Cloudflare R2 Pipeline Enhancement

Goal: Enhance the existing GitHub Actions pipeline with Cloudflare Workers for automated, event-driven processing. Keep the current GitHub Actions workflow untouched while building a parallel R2-native pipeline.

Duration: 1-2 weeks

Primary tools: Claude Code (for writing Workers), Wrangler CLI (for deployment), Claude Chat MCP (for R2 bucket operations)

## Step 1.1: Organize R2 Bucket Structure

Create a structured bucket layout that supports multi-state data at scale. Use Claude Chat with the Cloudflare MCP connector to create buckets interactively, or use Wrangler CLI.

[Claude Chat MCP] Use the Cloudflare Developer Platform connector to create R2 buckets directly from chat

[Wrangler CLI] wrangler r2 bucket create <bucket-name>

Recommended bucket structure:

crash-lens-raw/          # Raw downloads from state APIs

{state}/YYYY/          # e.g., virginia/2025/

crash-lens-validated/    # Post-validation clean data

{state}/YYYY/          # Same structure

crash-lens-exports/      # User-facing exports, reports

TIP: Use one bucket per lifecycle stage (raw, validated, exports) rather than one bucket per state. This simplifies lifecycle policies and access control.

## Step 1.2: Create the Download Worker

Build a Cloudflare Worker that downloads crash data from state APIs one state at a time on a cron schedule. This runs in parallel with your existing GitHub Actions pipeline during the transition period.

[Claude Code] Write the Worker code directly in your GitHub repo. Claude Code can access your existing download logic and adapt it.

Worker responsibilities:

- Accept a state code parameter (from cron trigger or manual invocation)

- Download crash data from that state's API endpoint

- Store raw data in R2 at crash-lens-raw/{state}/{year}/{filename}

- Update a metadata JSON in R2 tracking last successful download per state

- Trigger the validation Worker via R2 event notification on successful upload

Wrangler configuration (wrangler.toml):

[triggers]

crons = ["0 2 * * 1"]  # Every Monday at 2 AM UTC

[[r2_buckets]]

binding = "RAW_BUCKET"

bucket_name = "crash-lens-raw"

WARNING: Cloudflare Workers have a 30s CPU limit (free) or 15min with Cron Triggers (paid). States requiring Playwright browser automation (like CDOT Colorado) must stay on GitHub Actions.

## Step 1.3: Create the Validation Worker

Build a second Worker that is triggered by R2 event notifications when new raw data lands. This Worker runs your crash validation engine logic.

[Claude Code] Port your existing validation logic from the GitHub Actions pipeline to a Worker-compatible format

Validation Worker responsibilities:

- Read raw data from R2 event notification payload

- Run validation rules: field completeness, date ranges, coordinate bounds, severity codes

- For states missing road names (like Delaware), attempt OSM enrichment via Overpass API

- Write validated data to crash-lens-validated/{state}/{year}/{filename}

- Write validation report/stats to a metadata file

- On success, trigger the Supabase loader (Phase 2 integration)

## Step 1.4: Configure R2 Event Notifications

Wire up R2 event notifications so that when raw data lands in the raw bucket, the validation Worker fires automatically.

[Wrangler CLI] Configure event notifications in wrangler.toml

[[r2_buckets]]

binding = "RAW_BUCKET"

bucket_name = "crash-lens-raw"

# Event notification triggers validation Worker

[[r2_buckets.event_notifications]]

type = "object-create"

queue = "crash-lens-validation-queue"

## Step 1.5: Keep GitHub Actions Running in Parallel

Do NOT remove your existing GitHub Actions pipeline. Run both pipelines simultaneously for at least 2-4 weeks. Compare outputs to verify the R2-native pipeline produces identical results.

- GitHub Actions continues downloading and processing as before

- R2 Workers run the same downloads independently

- Compare validated output files between both pipelines

- Only decommission GitHub Actions download steps after validation passes for all active states

TIP: States that require Playwright browser scraping (CDOT Colorado) will remain on GitHub Actions permanently. The R2 Worker pipeline handles API-based states only.

PHASE 2

# Supabase Setup + Database Schema Design

Goal: Create the Supabase project, design the multi-state crash data schema with table partitioning, configure Row Level Security for multi-tenant access, and build the R2-to-Supabase data loader.

Duration: 1 week

Primary tools: Claude Chat MCP (Supabase connector for interactive SQL), Supabase CLI (for migrations), Claude Code (for loader script)

## Step 2.1: Create Supabase Project

Create a new project on Supabase Cloud (supabase.com). Start with the Pro plan ($25/month) for adequate database size and connection limits.

[Claude Chat MCP] Use the Supabase connector to create the project and run schema SQL directly from this chat

Save these credentials securely:

- Project URL (e.g., https://xxxx.supabase.co)

- anon key (public, used in frontend)

- service_role key (secret, used in backend/migration scripts only)

- Database password

- Direct database connection string (for pg_dump/pg_restore)

## Step 2.2: Design Multi-State Crash Data Schema

Design the PostgreSQL schema with partitioning by state for efficient queries at 50-state scale.

[Claude Chat MCP] Execute CREATE TABLE statements directly via the Supabase connector

Core tables:

-- Crashes table partitioned by state

CREATE TABLE crashes (

id UUID DEFAULT gen_random_uuid() PRIMARY KEY,

state_code CHAR(2) NOT NULL,

crash_date DATE NOT NULL,

latitude NUMERIC(10,7),

longitude NUMERIC(10,7),

severity TEXT,

county_fips CHAR(5),

mpo_id TEXT,

road_name TEXT,

total_vehicles INTEGER,

total_injuries INTEGER,

total_fatalities INTEGER,

raw_data JSONB,  -- Original state-specific fields

created_at TIMESTAMPTZ DEFAULT now()

) PARTITION BY LIST (state_code);

-- Create partition for each state

CREATE TABLE crashes_va PARTITION OF crashes

FOR VALUES IN ('VA');

CREATE TABLE crashes_co PARTITION OF crashes

FOR VALUES IN ('CO');

-- Repeat for each state...

-- Supporting tables

CREATE TABLE user_profiles (

id UUID REFERENCES auth.users PRIMARY KEY,

email TEXT,

organization TEXT,

state_code CHAR(2),

jurisdiction_type TEXT,  -- 'state', 'mpo', 'county'

jurisdiction_id TEXT,

tier TEXT DEFAULT 'free_trial'

);

-- Indexes for performance

CREATE INDEX idx_crashes_date ON crashes (crash_date);

CREATE INDEX idx_crashes_county ON crashes (county_fips);

CREATE INDEX idx_crashes_mpo ON crashes (mpo_id);

CREATE INDEX idx_crashes_geo ON crashes USING GIST (

ST_SetSRID(ST_MakePoint(longitude, latitude), 4326)

);

## Step 2.3: Configure Row Level Security (RLS)

RLS ensures each user only sees crash data for their jurisdiction. This is critical for multi-tenant B2G access.

ALTER TABLE crashes ENABLE ROW LEVEL SECURITY;

CREATE POLICY "Users see their state data"

ON crashes FOR SELECT USING (

state_code = (

SELECT state_code FROM user_profiles

WHERE id = auth.uid()

)

);

-- Agency tier: see full state

-- Team tier: see their MPO/county

-- Free trial: limited rows

TIP: RLS means your frontend code is simply: supabase.from('crashes').select('*') and each user automatically gets filtered data. No backend authorization logic needed.

## Step 2.4: Build the R2-to-Supabase Loader

Create a Cloudflare Worker (or extend the validation Worker) that loads validated crash data from R2 into Supabase PostgreSQL.

[Claude Code] Write the loader Worker in your GitHub repo

The loader reads validated CSV/JSON files from R2, transforms records into the normalized schema, and upserts into Supabase using the service_role key. Use batch inserts (1000 rows at a time) for performance.

WARNING: The service_role key bypasses RLS. Store it as a Cloudflare Worker secret (wrangler secret put SUPABASE_SERVICE_KEY), never in code.

## Step 2.5: Test the Full Pipeline

Run a complete test with Virginia data: GitHub Actions downloads raw data, uploads to R2, Worker validates and normalizes, loader pushes to Supabase, frontend queries via PostgREST.

- Verify row counts match between R2 validated files and Supabase tables

- Test RLS by logging in as different user profiles with different jurisdictions

- Measure query performance on county-level and MPO-level filters

PHASE 3

# Firebase to Supabase Auth Migration

Goal: Migrate all Firebase Auth users (email/password + Microsoft OAuth) to Supabase Auth with zero password resets required. Update the CRASH LENS frontend to use Supabase SDK.

Duration: 1-2 weeks

Primary tools: Claude Code (frontend code changes), firebase-to-supabase scripts (official migration tools), Supabase Dashboard (OAuth config)

## Step 3.1: Export Firebase Auth Credentials

You need three things from Firebase before anything else.

### A. Generate Firebase Service Account Key

Firebase Console > Project Settings > Service Accounts > Firebase Admin SDK > Generate New Private Key. Rename to firebase-service.json.

### B. Get Password Hash Parameters

Firebase Console > Authentication > Users > Menu (3 dots) > Password Hash Parameters. Copy and save: base64_signer_key, base64_salt_separator, rounds, mem_cost.

WARNING: These hash parameters are essential. Without them, users will be forced to reset passwords. Save them in a secure location.

### C. Export Users to JSON

git clone https://github.com/supabase-community/firebase-to-supabase.git

cd firebase-to-supabase/auth

npm install

# Place firebase-service.json in this directory

node export.js

This creates a JSON file with all users, their emails, and encrypted password hashes.

## Step 3.2: Import Users into Supabase

Configure the Supabase connection and run the import script.

[Supabase Dashboard] Get your database connection string from Settings > Database > Connection string (Session pooler)

# Configure supabase-service.json with your project credentials

# Then run the import

node import.js

Users are imported with their existing password hashes. Supabase can verify Firebase's scrypt hashes natively, so users log in with their existing passwords seamlessly.

## Step 3.3: Configure Microsoft OAuth in Supabase

Since CRASH LENS uses Microsoft OAuth for government agency users, configure Azure AD in Supabase.

- Supabase Dashboard > Authentication > Providers > Enable Azure (Microsoft)

- Enter your existing Azure AD Client ID and Client Secret (same ones from Firebase)

- Set the Tenant URL for your Azure AD directory

- Update the redirect URI in Azure Portal to: https://<your-project>.supabase.co/auth/v1/callback

- Test Microsoft SSO login with a test account

WARNING: The redirect URL change in Azure AD is the most commonly missed step. Double-check this before go-live.

## Step 3.4: Update Frontend Code

Replace Firebase SDK calls with Supabase client calls throughout the CRASH LENS frontend. Use Claude Code for this since it can see your entire codebase and make systematic changes.

[Claude Code] Run in your CRASH LENS repo. Give it the prompt: 'Replace all Firebase Auth SDK usage with Supabase Auth. Keep the same UX flow.'

Key code changes:

Install: npm install @supabase/supabase-js

Initialize: Replace initializeApp(firebaseConfig) with createClient(SUPABASE_URL, SUPABASE_ANON_KEY)

Sign In: Replace signInWithEmailAndPassword() with supabase.auth.signInWithPassword()

Microsoft OAuth: Replace OAuthProvider('microsoft.com') with supabase.auth.signInWithOAuth({ provider: 'azure' })

Auth Listener: Replace onAuthStateChanged() with supabase.auth.onAuthStateChange()

Sign Out: Replace auth.signOut() with supabase.auth.signOut()

Token Format: Update any Cloudflare Workers that validate Firebase JWTs to validate Supabase JWTs instead

## Step 3.5: Run Both Auth Systems in Parallel

Deploy the Supabase Auth version to a staging environment first. Run both Firebase and Supabase auth for 1-2 weeks.

- Week 1: Deploy to staging, test all auth flows (email, Microsoft OAuth, password reset)

- Week 2: Deploy to production, monitor for auth failures

- Week 3: If no issues, remove Firebase SDK and shut down Firebase project

TIP: Keep Firebase running until you are 100% confident Supabase Auth is working. The cost of running both simultaneously for a few weeks is negligible compared to the risk of locking users out.

PHASE 4

# Coolify Migration: Hostinger to AWS EC2

Goal: Launch an AWS EC2 instance, install Coolify, restore all configurations and application data from Hostinger, and cut over DNS.

Duration: 1 week

Primary tools: AWS Console (or Terraform), SSH/SCP, Coolify Dashboard

## Step 4.1: Launch AWS EC2 Instance

Create the EC2 instance that will become your new Coolify host.

[AWS Console] Launch instance manually, or use Terraform for reproducibility

| Setting | Value |
| --- | --- |
| AMI | Ubuntu 24.04 LTS |
| Instance Type | t3.medium (2 vCPU, 4GB RAM) — upgrade to t3.large if running databases |
| Storage | 50GB gp3 EBS (expandable without downtime) |
| Elastic IP | Allocate and attach (static IP that survives stop/start) |
| Key Pair | Create new or use existing SSH key pair |
| Region | us-east-1 (Virginia) — closest to your location and users |

Security Group rules:

| Port | Protocol | Source | Purpose |
| --- | --- | --- | --- |
| 22 | TCP | Your IP only | SSH access |
| 80 | TCP | 0.0.0.0/0 | HTTP |
| 443 | TCP | 0.0.0.0/0 | HTTPS |
| 8000 | TCP | Your IP only | Coolify dashboard |
| 6001 | TCP | Your IP only | Coolify WebSocket |

TIP: Use Terraform if you want this to be reproducible. But for a single server, the AWS Console is faster for a one-time setup.

## Step 4.2: Install Coolify on EC2

ssh -i your-key.pem ubuntu@<elastic-ip>

sudo apt update && sudo apt upgrade -y

curl -fsSL https://cdn.coollabs.io/coolify/install.sh | sudo bash

Wait for installation to complete (5-10 minutes). Access Coolify at http://<elastic-ip>:8000 and register admin account.

WARNING: Do NOT configure anything in the new Coolify yet. You will restore from backup in the next step.

## Step 4.3: Backup Everything on Hostinger

SSH into your Hostinger server and collect four items:

### A. Coolify Database Backup

Coolify Dashboard > Settings > Backup tab > Backup Now > Download

### B. APP_KEY

cat /data/coolify/source/.env | grep APP_KEY

Save this value securely. Without it, you cannot restore the backup.

### C. SSH Keys

scp -r root@<hostinger-ip>:/data/coolify/ssh/keys ./coolify-ssh-backup/

### D. Docker Volumes (Application Data)

For each application with persistent data:

docker run --rm -v <volume_name>:/data -v /tmp/backups:/backup \

alpine tar czf /backup/<volume_name>.tar.gz -C /data .

scp root@<hostinger-ip>:/tmp/backups/* ./volume-backups/

## Step 4.4: Restore on AWS EC2

### A. Transfer Files

scp coolify-backup.dmp ubuntu@<ec2-ip>:/tmp/

scp -r coolify-ssh-backup/* ubuntu@<ec2-ip>:/data/coolify/ssh/keys/

scp volume-backups/* ubuntu@<ec2-ip>:/tmp/backups/

### B. Restore Coolify Database

cat /tmp/coolify-backup.dmp | docker exec -i coolify-db \

pg_restore --verbose --clean --no-acl --no-owner -U coolify -d coolify

### C. Update APP_KEY

nano /data/coolify/source/.env

# Add: APP_PREVIOUS_KEYS=<your-old-app-key-value>

### D. Restore Docker Volumes

docker volume create <volume_name>

docker run --rm -v <volume_name>:/data -v /tmp/backups:/backup \

alpine sh -c "cd /data && tar xzf /backup/<volume_name>.tar.gz"

### E. Restart Coolify

cd /data/coolify/source

docker compose down && docker compose up -d

Verify all applications appear in the Coolify dashboard and redeploy each one.

## Step 4.5: Update DNS and Cut Over

Update your Cloudflare DNS A records from the Hostinger IP to the new AWS Elastic IP.

- Update A record for your main domain to the AWS Elastic IP

- If using Cloudflare Tunnel, create a new tunnel on the EC2 instance: cloudflared tunnel create crash-lens-aws

- Verify SSL certificates are provisioned (Coolify handles Let's Encrypt automatically)

- Run both servers in parallel for 48-72 hours before shutting down Hostinger

TIP: Lower your DNS TTL to 60 seconds a few days before the cutover. This ensures the DNS change propagates quickly. Raise it back to 3600 after stable.

PHASE 5

# Integration Testing + Go-Live

Goal: Connect all migrated components into a unified system, run end-to-end tests, and go live with the new infrastructure.

Duration: 1-2 weeks

Primary tools: All tools (Claude Code for final integration, Claude Chat for testing, browser for manual QA)

## Step 5.1: End-to-End Pipeline Test

Run the complete data flow from state API to user dashboard:

- GitHub Actions downloads Virginia crash data

- Data uploads to Cloudflare R2 (crash-lens-raw/va/2026/)

- R2 event notification triggers Validation Worker

- Validation Worker processes data, writes to crash-lens-validated/

- Loader Worker reads validated data, upserts into Supabase PostgreSQL

- User logs in via Supabase Auth (Microsoft OAuth)

- Frontend queries Supabase with RLS — user sees only Henrico County data

- CRASH LENS dashboard renders crash map with Mapbox

## Step 5.2: Performance and Security Audit

Before going live with government customers, verify these critical items:

- Database query performance: County-level queries return in < 500ms

- RLS is enforced: No user can see data outside their jurisdiction

- Auth tokens are validated correctly by all Workers

- Supabase service_role key is never exposed to the frontend

- R2 bucket permissions are correctly scoped (no public write access)

- SSL/TLS is enforced on all endpoints

- Coolify on AWS has automated daily backups configured

## Step 5.3: Stripe Billing Integration Update

Update your Stripe webhook endpoints to point to the new AWS infrastructure. Verify that the four pricing tiers (Free Trial, Individual, Team, Agency) still map correctly to Supabase user profiles and RLS policies.

[Claude Code] Update webhook endpoint URLs in your Stripe configuration and verify tier-to-RLS mapping

## Step 5.4: Decommission Old Infrastructure

Only after 2 weeks of stable operation on the new stack:

- Shut down Firebase project (Authentication section)

- Cancel Hostinger VPS subscription

- Remove Firebase SDK from frontend codebase entirely

- Archive old GitHub Actions workflows that have been replaced by Workers

WARNING: Keep Hostinger running for at least 2 full weeks after DNS cutover. If any issues arise, you can revert DNS in minutes.

## Step 5.5: Document the New Architecture

Update your project documentation to reflect the new stack. This is important for onboarding Subhash and Atikur, and for any future government security reviews.

- Architecture diagram showing: AWS EC2 > Coolify > CRASH LENS Frontend

- Data flow diagram: State APIs > GitHub Actions > R2 > Workers > Supabase > Frontend

- Credential inventory: Where each API key, service account, and secret is stored

- Backup procedures: Coolify database, Supabase database, R2 data

- Incident response: What to do if each component fails

# Monthly Cost Comparison

Estimated monthly costs for the current vs target infrastructure at initial scale (1-5 states, < 50 users):

| Service | Current Cost | Target Cost |
| --- | --- | --- |
| Hosting (Coolify) | $10-15/mo (Hostinger VPS) | $30/mo (AWS t3.medium on-demand) |
| Database | $0 (no database) | $25/mo (Supabase Pro) |
| Auth | $0 (Firebase free tier) | $0 (included in Supabase Pro) |
| Storage (R2) | ~$1-5/mo | ~$1-5/mo (unchanged) |
| Cloudflare Workers | $0-5/mo | $5/mo (Workers Paid plan) |
| GitHub Actions | $0 (free tier) | $0 (reduced usage) |
| Domain / DNS | $0 (Cloudflare) | $0 (Cloudflare) |
| TOTAL | ~$15-25/month | ~$60-65/month |

The ~$40/month increase gets you: a queryable database layer, auto-generated APIs, multi-tenant auth with RLS, AWS hosting for government credibility, and a scalable architecture that handles 50 states. This cost is trivially covered by a single Agency-tier subscription ($299+/month).

# Ready-to-Use Claude Code Prompts

Copy-paste these prompts into Claude Code when working on each phase. Each prompt gives Claude Code the context it needs to make the right changes in your repo.

Phase 1 — Create Download Worker:

Create a Cloudflare Worker in src/workers/download-worker.ts that:

1. Accepts a state_code parameter from cron trigger

2. Reads the state API endpoint from a config JSON in R2

3. Downloads crash data from that state's API

4. Stores raw data in R2 bucket 'crash-lens-raw' at

{state_code}/{year}/{filename}

5. Updates metadata.json tracking last download timestamp

Include wrangler.toml config with cron trigger and R2 binding.

Phase 1 — Create Validation Worker:

Create a Cloudflare Worker in src/workers/validation-worker.ts that:

1. Triggers on R2 event notification from crash-lens-raw bucket

2. Reads the uploaded file from R2

3. Validates fields: lat/lon bounds, date ranges, severity codes,

required fields (crash_date, state_code, coordinates)

4. For records missing road names, enrich via Overpass API

5. Writes validated data to 'crash-lens-validated' bucket

6. Writes validation report with pass/fail counts

Use the existing validation rules from our current pipeline.

Phase 3 — Replace Firebase Auth:

Replace all Firebase Auth SDK usage with Supabase Auth across

the entire CRASH LENS frontend. Specifically:

1. npm install @supabase/supabase-js

2. Create src/lib/supabase.ts with createClient()

3. Replace initializeApp with createClient

4. Replace signInWithEmailAndPassword with

supabase.auth.signInWithPassword

5. Replace OAuthProvider('microsoft.com') with

supabase.auth.signInWithOAuth({ provider: 'azure' })

6. Replace onAuthStateChanged with

supabase.auth.onAuthStateChange

7. Replace auth.signOut with supabase.auth.signOut

8. Update any Workers that validate Firebase JWTs to

validate Supabase JWTs

Keep the same UX flow. Do not change any UI components.

# Master Migration Checklist

Use this checklist to track progress across all phases.

Phase 1: Cloudflare R2 Pipeline

- R2 buckets created (raw, validated, exports)

- Download Worker written and tested with Virginia data

- Validation Worker written with OSM enrichment for missing road names

- R2 event notifications configured

- Cron trigger configured for weekly downloads

- Parallel run with GitHub Actions verified (matching outputs)

Phase 2: Supabase Setup

- Supabase project created on Pro plan

- Crashes table created with state partitioning

- user_profiles table created

- PostGIS extension enabled for geospatial queries

- Row Level Security policies configured and tested

- R2-to-Supabase loader Worker built and tested

- Virginia data loaded into Supabase and queryable from frontend

Phase 3: Firebase to Supabase Auth

- Firebase service account key exported

- Password hash parameters saved

- Users exported to JSON via migration tool

- Users imported into Supabase auth.users table

- Microsoft OAuth configured in Supabase (Azure provider)

- Azure AD redirect URI updated to Supabase callback

- Frontend code updated: all Firebase SDK calls replaced with Supabase

- Staging deployment tested with email + Microsoft OAuth login

- Production deployment with parallel auth (2 week overlap)

- Firebase project decommissioned

Phase 4: Coolify to AWS

- AWS EC2 instance launched (t3.medium, Ubuntu 24.04, us-east-1)

- Elastic IP allocated and attached

- Security group configured (ports 22, 80, 443, 8000, 6001)

- Coolify installed on EC2

- Coolify database backup exported from Hostinger

- APP_KEY saved securely

- SSH keys transferred

- Docker volumes backed up and transferred

- Coolify database restored on EC2

- All applications redeployed and verified

- DNS updated in Cloudflare (A record to Elastic IP)

- SSL certificates provisioned

- 48-72 hour parallel run completed

- Hostinger decommissioned

Phase 5: Integration + Go-Live

- End-to-end pipeline test passed (State API to user dashboard)

- RLS verified (users only see their jurisdiction)

- Query performance acceptable (< 500ms for county-level queries)

- Stripe billing webhooks updated to new infrastructure

- Automated backups configured for Coolify and Supabase

- Architecture documentation updated

- Credential inventory documented and shared with partners